## Topics_Working_On_with_Descript
Tasks | Description | Priority/Order | Start date | Target/Date | Status | Subramanya
End/of/Line (EOL) Release Testing | Performing EOL tests for all releases. | 1 | 2025-03-13 | 2025-04-11 | Completed | 100%
XTS Framework Development | Developing and maintaining the XTS framework. | 2 | 2025-03-13 | 2025-04-11 | Completed | 100%
Automator and XTS Integration | Making XTS work with Automator to remove manual inputs and use Automator’s parameters directly. | 3 | 13/3/2025 | 2025-11-04 | Completed | 100%
MAC/Level Ethernet Communication | Writing Python scripts to enable communication between the target and tester MAC addresses. | 4 | 2025-07-04 | 2025-11-04 | Completed | 100%
CANoe Communication using CAPL | Writing CAPL scripts to test CAN echo and CAN FD frames. | 5 | 2025-08-04 | 2025-11-04 | Completed | 100%
GoogleTest for Bootloader Unit Tests and Coverage Report | Writing unit tests for the bootloader and QuadSPI using GoogleTest and generating coverage reports. | 9 | 17/4/2025 |  | Completed | 100%
Base Image Refactoring | Reducing base packages to improve boot time. | 7 | 2025-04-09 | 2025-04-09 | Completed | 100%
Flasher App Testing | Testing and validating the flasher application. | 8 | 2025-04-02 | 2025-04-04 | Completed | 100%
B2 App Image Requirements Documentation | Writing requirements using Docs/as/Code. | 10 | 2025-03-20 | 2025-04-08 | Completed | 100%
Boot Time Calculation and Graph Generation | Writing Python scripts to measure boot time using timer functions and PicoScope, then generating graphs for analysis. | 6 | 15/4/2025 |  | Completed | 100%

## Daily_sync
Date | Hours Spent | Topics | Description
13/03/2025 | 2 | Automator | Basic understanding on how to run the automator for smoke tests and made documentation on automator running process
17/03/2025 | 3 | XTS Framework | Basic understanding on how to run the XTS Framework for eol tests with and without the automator and made documentation on how to run xts framework
18/03/2025 | 2.5 | XTS Framework | Hands on xts framework to build and see the reports(only test_scripts, not the automator)
19/03/2025 | 2 | Automator | Debug sessions on issues with xts framework
20/03/2025 | 3 | Requirements-docsascode | Explanation on how sphinx is used to write rst files for requirements, test case specifications
21/03/2025 | 3 | Documentation for docsascode | worked on documentation for sphinx use in the project
24/03/2025 | 3 | Debug sessions on Automator | worked on debugging issues with eol tests
25/03/2025 | 2 | Understanding automator code | Understanding automator code
26/03/2025 | 3 | Understanding automator code | Understanding automator code
2025-01-04 | 3 | Understanding automator code | Understood state machine working and did a few changes on the yocto gui
2025-02-04 | 3 | Flasher app explanation | Understood how flasher app works, but couldnt perform a demo since in none of setups tftp was reliable
2025-03-04 | 3 | Understanding XTS Framework code | Understood build.ps1 and the flow of send.py and ran it once
2025-07-04 | 3 | Ethernet test understanding | understood how ethernet is communicating on the mac level with xts
2025-08-04 | 3 | Canoe understanding | understood how canoe works with xts
2025-09-04 | 1.5 | Canoe understanding | understood the flow of send.py to execute canoe tool and set env variable
2025-09-04 | 1.5 | Base image refactoring | Understood how to reduce packages in the base image
15/4/2025 | 3 | Boot time graph understanding | Understood how boot_time_graph.py
16/4/2025 | 3 | Boot time demo and documentation | Demo for boot_time_graph.py and made documentatation
17/4/2025 | 3 | Google test configuration understanding | Understood how to include gtest in cmake project
21/4/2025 | 3 | Gcovr understanding | Understood how gcovr works generating of executable for unit tests
22/4/2025 | 3 | Coverage report demo | Performed a live demo for setting up gtest with a few unit tests and generated the coverage report
23/4/2025 | 3 | Gtest documentation | Worked on documentation for gtest and gcovr with a cmake project from scratch
24/4/2025 | 3 | Documentation and hands on | worked on gtest documentation and hands on gtest repo, pushed everything to repo